Las Positas College- Office of Academic Services

SCHEDULE TIMELINE

Spring 2019

7.5.18

This timeline is provided to keep track of the mandatory dates to make necessary changes to the Spring 2019 Schedule.  Please submit all changes, edits and adjustments by the timeline dates. Schedule Production Deadlines:

May

Wed    5.23.18	               1st Draft Sent to Division Deans

June

Thurs   6.21.18		1st Draft Edits Due to Scheduler (Andrea. M)

July

Thurs   7.5.18		2nd Draft Sent to Division Deans

August

Thurs   8.2.18		2nd Draft Edits Due to Scheduler

Thurs    8.9.18		3rd Draft sent to the Division Deans

September

Thurs    9.6.18		3rd Draft Edits Due to Scheduler (Andrea. M)

Thurs   9.13.18                   Word Doc sent to Division Deans

Thurs   9.20.18                    Word Doc Edits due to Scheduler (Andrea. M) by 2PM

Design Process

Thurs   9.20.18	               Scheduler sends Word Doc to the Designer (Cheryl)

TBA                 	 	Design Copy sent to Scheduler  Divisions

TBA                     	Divisions Return Design Copy Corrections to the Scheduler by 2PM

TBA			 Scheduler sends Design Copy corrections to Designer

TBA                      	 Designer uploads files via FTP to Wesco (print)

Printing Process

TBA    			 Final Print Draft sent to Designer  Scheduler  Divisions

TBA              		Wesco sends the Blueline to the Designer  Scheduler  Divisions

TBA  	 	 	Corrections to the Blueline due to the Scheduler by 12 noon to the Designer by 1pm

TBA    		 	Printed Schedules are Delivered to LPC

SPRING 2019- PRIORITY REGISTRATION BEGINS TBA