## Sheet1
LAS POSITAS COLLEGE
PROGRAM REVIEW - PLANNING CYCLE
College-wide planning cycles | [8 empty] | 2005 - 2015
|  | Fall 05 | Spring 06 | Fall 06 | Spring 07 | Fall 07 | Spring 08 | Fall 08 | Spring 09 | Fall 09 | Spring 10 | Fall 10 | Spring 11 | Fall 11 | Spring 12 | Fall 12 | Spring 13 | Fall 13 | Spring 14 | Fall 14 | Spring 15
Accreditation
| Focus Groups |  |  |  |  | Foc. Grps
| Survey |  |  |  |  | Survey
| write | [5 empty] | Write | Write
| visit | [8 empty] | Visit
Master Plan
| Write |  |  |  | WRITE | [6 empty] | WRITE | [7 empty] | WRITE
| Update | [5 empty] | UPDATE |  | UPDATE |  | UPDATE |  | UPDATE |  | UPDATE |  | UPDATE |  | UPDATE |  | UPDATE
Program Review
| Review All | [8 empty] | WRITE | VALIDATE | [6 empty] | WRITE | VALIDATE
| Acad Sen | [6 empty] | Review | Approval
| Update |  |  |  |  | UPDATE(SLO) |  | UPDATE (Curric) |  |  |  | UPDATE |  | UPDATE |  | UPDATE |  |  |  | UPDATE
SLO
| Implementation |  |  |  | Vanguards | Planning Cycle | Cycle 1 | Cycle 2 | Cycle 3
| Reflection and Planning | [7 empty] | Reflect/ Evaluate/ Change

## SLO Grid
General SLO Timeline
F07 (Accred Surveys) | S08 (Self Study) | F08 (Self-Study) | S09 (Re-visit SLO Plan) | F09 (Site Visit) (Prog Rev) | S10 (Prog Rev) | F10
Plan 10 courses | Implement courses 1&2 | Implement courses 1-4 | Implement courses 4-8 | Implement courses 6-10 | Implement courses 8-12 | Implement courses 10-14
1.write SLOs for course | 1. Run Assessment
2. Design assessment(s) | 2. Generate results/recommendations |  | If fewer that 8 courses
3. Develop rubric | 3. Enter into elumen |  | Rerun courses1&2
4. Enter into Elumin | 4. Feedback loop
| Plan courses 11&12 | Plan courses 13&14 | Plan courses 15&16 | Plan courses 17&18 | Plan courses 19-20
General Plan: All disciplines will use Fall 2007 to plan their assessment for 10 courses
Plan = 1. writing Slo for course 2. Design assessment(s) 3. Create rubric 4. enter into eLumen
Implement = Run assessment 2. Generate results/recommendations 3. Enter into Elumin 4. Feedback loop
Disciplines will Implement 4 course each semester
Two will be new implementations
2 will be repeats
Courses will be rotated.
Each course is Implements for 2 semesters after which it is rotated out and will re-assessed once all other course have been implemented.